## Cover page
SHARING ECONOMY PLATFORM
Unit Test Cases & Log Template
1
|  | Prepared By / Last Updated by | Test case Reviewed by | Test Log Reviewed By | Approved By
| Name | S.Vishnupriya,R.Sivaranjini | Mohamed Raffic | Mohamed Raffic | Mohamed Raffic
| Role | Team Member | Trainer | Trainer | Scrum Master
| Signature | S.Vishnupriya,R.Sivaranjini
| Date | 2019-06-19 | 2019-06-19 | 2019-06-19 | 2019-06-19
| Project ID:<AJ_Project 7> |  |  |  | <SCI.ID.> / Ver: <Ver No.>
| Release ID: QTAD-UTCX / 8.1.0 / 23-Apr-12 |  |  |  | C3: Protected
Controlled copy
C3 Protected
Controlled copy
C3 Protected
Controlled copy
Controlled copy

## Test Case details
Unit Test Cases & Log Template - Test Case details Sharing Economy Platform Release ID: QTAD-UTCX / 8.1.0 / 23-Apr-12 C3: Protected Controlled Copy Project ID:<AJ_Project 7.> <SCI.ID.> / Ver: <Ver No.>
Test Cases and Log
Test Type : | Unit Testing | Version Number
Author: | S.Vishnupriya | Date: | 19/06/2019
Purpose & Scope:
1. User / Vendor being able to access the homepage & get redirected to the ‘User Registration’ / 'Vendor Registration' page upon click of ‘Register' link. 2. A registered user / vendor – is able click ‘Login’ link, after keying in ‘UserID’/ 'VendorUserID & ‘Password’ field and get his credentials authenticated with the existing database entry. 3. User able to select the Service or Product. 4. Vendor able to update Vendor Details. 5. Vendor able to select Service or Product. 6. Vendor able to update Service/ Product details. 7. Vendor able to edit / delete the product or service.
Test Pre-requisites:
Sharing Economy Platform- Homepage availability & access Sharing Economy Platform- Ability to navigate between sessions Sharing Economy Platform-Vendor / User accessibility.
File Naming & Versioning Conventions
1) The version of the file is tied to the version of the test cases document and not the log. 2) When there is a revision in the test cases document, the version number of the cases document is changed. 3) Test runs must be tied to the test cases document version and must be suffixed with the run number. 4) This differentation is important as the cases document and the log has been combined in this template. Eg: Mod1_Test_Proc1_1.0 is the test cases document version and Mod1_Test_Proc1_1.0_Run1 is the first run for this Test cases document 5) If the test case passes, then PASS may be indicated against the test case. 6) If it fails, then FAIL must be indicated and the defect ID needs to be filled up 7) Defect Tracking is a separate template that could be combined for version / runs of test cases document and logs. The differentiation of version/ run is implemented by filling up the same in the defect tracking template.

## Test Cases & Log
Unit Test Cases & Log Template - Test Cases & Log SHARING ECONOMY PLATFORM Release ID: QTAD-UTCX / 8.1.0 / 19/4/2019 C3: Protected Controlled Copy Project ID:<AJ_Project 7> <SCI.ID.> / Ver: <Ver No.>
Test Cases and Log
Test Procedure Name | Run Number | Testing done by | Signature | Date
GI_PH_UnitTC | 1 | S.Vishnupriya | S.Vishnupriya | 2019-06-19
[5 empty] | Run Number 1 |  |  | Run Number 2 |  |  |  |  | Run Number 3 |  |  |  | Run Number 4 |  |  |  | Run Number 5
Test Case ID | Test Case | Test Case Type | Steps to execute the test case | Expected Result | Actual Result | PASS / FAIL | Defect ID | Remarks | Actual Result | PASS / FAIL | Defect ID | Remarks | Actual Result | PASS / FAIL | Defect ID | Remarks | Actual Result | PASS / FAIL | Defect ID | Remarks | Actual Result | PASS / FAIL | Defect ID | Remarks
Sharing Economy Platform / Registration or Login
1 | Verify if the homepage is accessible | Positive | Access the homepage link provided | Home page should be displayed | Home page is displayed | PASS
2 | Verify if the User/ Vendor Registration Page is accessible | Positive | Click 'Register' link | User/ Vendor should be able to view the User Registration page and Vendor should be able to view the Vendor Registration page | User Redirected to User Registration page and Vendor Redirected to Vendor Registration page. | PASS
3 | Verify the user validations or Vendor validations. | Positive | Clicking 'submit' should validate the datatype constraints for each field | Post-successful field level validation,should save the information in the database | The information is stored in the database | PASS
4 | User / Vendor failing to provide information on the mandatory fields should be provided with an alert message | Negative | Clicking 'submit' should validate the datatype constraints for each field | Upon failing to check the mandatory fields should produce an alert message | Alert message is displayed | PASS
5 | A registered user – is able to click ‘Login’ link, after keying in ‘UserID' & ‘Password’ field and get his credentials authenticated with the existing database entry and A registered Vendor – is able to click ‘Login’ link, after keying in ‘VendorUserID' & ‘Password’ field and get his credentials authenticated with the existing database entry. | Positive | Clicking 'submit' should validate the datatype constraints for each field and must check with the existing database entry. | Login Page should be displayed | Login Page is displayed | PASS
6 | If a registered user – is unable to login and get his credentials authenticated, The user is presented with relevant error messages:Invalid User ID (or) Incorrect Password | Negative | Clicking 'submit' should validate the datatype constraints for each field and must check with the existing database entry. | Upon failing to check the mandatory fields should produce an alert message | Alert message is displayed | PASS
7 | If a registered Vendor – is unable to login and get his credentials authenticated, The Venndor is presented with relevant error messages:Invalid VendorUserId (or) Incorrect Password | Negative | Clicking 'submit' should validate the datatype constraints for each field and must check with the existing database entry. | Upon failing to check the mandatory fields should produce an alert message | Alert message is displayed | PASS
Sharing Economy Platform / Login / User Sessions
8 | Logged in user can able to select the Service or Product | Positive | Upon correct validation, the user must be able to navigate between different sessions. | Approporiate selection and navigation between sessions | User is able to navigate between sessions | PASS
9 | Based on the user selection, display the categories available for the Products / Services | Positive | Upon user selection, the categories available for the Products / Services should be displayed. | Details to be successfully displayed. | Details are displayed sucessfully. | PASS
10 | Based on the Product / Service selected, display the item details and the Vendor details | Positive | Upon Product / Service selection, the the item details and the Vendor details should be is displayed. | All the item details and the Vendor details are displayed. | Details Displayed sucessfully. | PASS
Sharing Economy Platform/ Login / Vendor Sessions
11 | Logged in vendor should be able to update his existing details | Positive | Upon clicking update the details should be updated in the database. | Details are Updated. | Updation done sucessfully. | PASS
12 | Vendor can able to select the Service or Product | Positive | Upon product / service selection, the Vedor must be able to navigate between different sessions. | Approporiate selection and navigation between sessions | Vendor able to navigate between sessions | PASS
13 | Vendor should be able to update his product details / service details | Positive | Upon selecting 'update' the Vendor should be able to update his product details / service details | Clicking 'update' should validate the datatype constraints for each field and save the information in the database. | Information is stored in database and Product/Service updated message is displayed | PASS
14 | Vendor should have the option to edit / delete the Product / Service details entered by them. | Positive | Upon selecting 'Delete' or 'Edit' the Vendor should be able to edit/delete the product details / service details | Clicking 'submit' should validate the datatype constraints for each field and save the information in the database. | Information is stored in database and Blood Count details recorded successfully message is displayed. | PASS
15 | Based on the category selected by the vendor the system should save the details of the product entered in the database. | Positive | on clicking 'Subm | Clicking 'submit' should display the chance of risk and save the information in the database. | Information is stored in databse and display the risk result on the screen | PASS
Sharing Economy Platform / Logout
16 | Ability of the system to allow the User / Vendor to logged out. | Positive | On selecting logout the vendor or user must be able to log out | Logout page displayed | Vendor / User sucessfully logged out. | PASS
Note on F6: Copy these set of columns (actual result, pass/fail, defect ID and Remarks) for every run. Note: if the test cases change between builds, these runs have to be logged against the revised set of test cases in a separate document.

## Change Log
Change Log
Please note that this table needs to be maintained even if a Configuration Management tool is used.
Version Number | Changes made
V1.0.0 | <First version>
V1.1.0 | <If the change details are not explicitly documented in the table below, reference should be provided here>
| Page No | Changed by | Effective Date | Changes Effected
V1.2.0 | <If the change details are not explicitly documented in the table below, reference should be provided here>
| Page No | Changed by | Effective Date | Changes Effected

## Compatibility Report
Compatibility Report for Sharing Economy Platform.xls
Run on 6/19/2019 15:42
If the workbook is saved in an earlier file format or opened in an earlier version of Microsoft Excel, the listed features will not be available.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 1 | Excel 97-2003